## Sheet1
Sprint Backlog
Activity | Date | Member Assigned
Sprint 1 | 6 jan - 10 jan
Wireframe diagrams | 2020-01-08 | Puneet, jawahar,yashul,Ujjwal,deepesh
Prepare Gui webpages | 2020-01-09 | Jawahar, yashul,puneet,deepesh
Link webpages | 2020-01-10 | Puneet, jawahar
Sprint 2 | 13 jan-17 jan
Login and register webpages | 2020-01-13 | puneet,deepesh,jawahar
Login and register database connectivity | 2020-01-15 | Puneet
Sprint 3
Webpages of Welcome screen, create project, available projects and open project
Database connectivity of the pages
Testing
Hosting the updated website
Sprint 4
Product Backlog, Sprint Backlog, upload deliverables webpages
Database connectivity of the pages
Testing
Hosting the updated website
Sprint 5
Create Meeting, upload deliverables, project progress webpages
Database connectivity of the pages
Testing
Hosting the updated website
Sprint 6
Finishing the website for mobile view
Testing the whole website
Hosting the updated website